## Cover Page
<ATM_MANAGEMENT_SYSTEM>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | MUNTHA BHARGAV
| Role | POD Leader
| Signature | MUNTHA BHARGAV
| Date | 2022-02-14
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog <ATM_MANAGEMENT_SYSTEM> Project ID: <ADM21DN013/POD-1> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | User Registration | 8
Task_1 | Create table for user registration |  | BHARGAV | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | MEGHANA | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Devlop code for User Registration Page |  | SOUMYAKANTA | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop code to store User Registration details |  | PAVITHRA | Completed | 0.5 | 1 | 2 | 3 | 1 | 0
User Story #2 | User Login | 1
Task_1 | Create table to store Login details |  | VASANTH KUMAR | Completed | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the User Login page |  | MEGHANA | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for User Login page |  | PAVITHRA | Completed | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the Login details |  | SOUMYAKANTA | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #3 | User Interface | 5
Task_1 | Develop code for User to view Account details |  | MEGHANA | Completed | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop code for User to Check their Account Balance |  | SOUMYAKANTA | Completed | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for User to Deposit an Amount into their Account |  | BHARGAV | Completed | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for User to Withdraw an Amount from their Account |  | VASANTH KUMAR | Completed | 2 | 0.5 | 0 | 0 | 0 | 0
User Story #4 | User Interface | 8
Task_1 | Develop code for User to change their Account Pin |  | PAVITHRA | Completed | 9 | 4 | 2 | 2 | 1 | 1
Task_2 | Develop code to Navigate the Pages |  | MEGHANA | Completed | 6 | 6 | 3 | 3 | 3 | 1
Task_3 | Develop code for User Validation |  | SOUMYAKANTA | Completed | 6 | 2 | 8 | 8 | 1 | 0
Task_4 | Develop code for User to update their Account Details |  | BHARGAV | Completed | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
User Story #5 |  | 3
Task_1 | Develop Code to store Updated details |  | MEGHANA | Completed | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 | Develop code to store Updated data in Database |  | SOUMYAKANTA | Completed | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 | Added Back Button |  | VASANTH KUMAR | Completed | 9 | 9 | 9 | 4 | 3 | 3
Task_4 | Added Logout Button |  | BHARGAV | Completed | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -2
Sprint Backlog <ATM_MANAGEMENT_SYSTEM> Project ID: <ADM21DN013/POD - 1> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | User Data | 8
Task_1 | User can Register with their Account Details |  | BHARGAV | Completed | 7 | 5 | 3 | 3 | 5 | 0
Task_2 | User can Login with their Account Details |  | MEGHANA | Completed | 3 | 2 | 4 | 5 | 0 | 1
Task_3 | Registered User can select the Transactions |  | SOUMYAKANTA | Completed | 5 | 1.5 | 3 | 6 | 4 | 2
Task_4 | User can check the Transaction details |  | VASANTH KUMAR | Completed | 7 | 3 | 2 | 7 | 1 | 1
User Story #2 | User Reort | 1
Task_1 | User can change their Pin |  | PAVITHRA | Completed | 4.5 | 3 | 2.5 | 3.5 | 2 | 3
Task_2 | User can check their Balnce before withdrwan |  | MEGHANA | Completed | 3 | 5 | 5 | 3 | 4 | 1
Task_3 | User can Deposit less than or equal to 1 lakh |  | SOUMYAKANTA | Completed | 4 | 4 | 5 | 2 | 5 | 3
Task_4 | User can Logout |  | BHARGAV | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 38.5 | 28.5 | 33.5 | 34.5 | 22 | 11

## Data (hidden)
In-Progress
Completed
N/A